## Guide
Workflow for scrum practices
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points (next module)
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## ProductBacklog
Product Backlog - Project Title
User Stroy | Story Point(s) | Priority
1. As an owner I want a platform that access the customers answers and compare them with candidate answers and recommend the 3 best matches. | N/R | 1/4
2. As a customer I should be able to go back and forth thought questionary and change my answers if needed before submit. |  | 1/4
3. As a customer I should see the result of my answers and suggested candidates with great user interface |  | 1/4
4. As a customer I should be able to see the Information of the candidates that have the best match with my answers with suitable user interface. |  | 1/4
5. As an owner I want to Candidate information and also candidates’ answers. |  | 1/4
6. as a customer I should see all candidates with full information. |  | 1/4
7. as an owner I need Create login page for admins which could be able to edit questions |  | 1/4 | Sprint 1
8. As an owner I should be able to create questionary, which customers can use it answer the questions. |  | 1/4 | Sprint 2
9. As a customer, I should be check my answers after finish my questionari |  | 2/4 | Sprint 3
10 . as a customer I need a navigation bar to access better throught pages |  | 2/4 | Sprint 4
11 - As a owner I need a enterance login for customer to save their information for future usage |  | 1/4
12. as an owner I need Create login page for admins which could be able to edit Candidates |  | 1/4
13 - as an owner I should be able to add new candidates with their answers |  | 2/4
14 - as a customer I need to see statistics of candidates results |  | 2/4
Write briefly about your project and implementation. You may list features:
We are creating a Hotel website, where customer can reserve a room, compare the prices of rooms. See the room details and other facilities.
Users can also subscribe a newsletter and give a feedback of reservation process.

## sprint_planning_meetings
Spring Planning | Participants
Week 1 | Saida | Hossein | Carlos | Ivan
Online | yes | yes | yes | yes
30.04.2021
Week 2- sprint1 | Hamza | Hossein | Carlos | Ivan
Online |  | yes
07.05.2021
Week 3 - sprint2 | Hamza | Hossein | Carlos | Ivan
Online |  | yes
15.05.2021
Week 4 - sprint3 | Hamza | Hossein | Carlos | Ivan
Online |  | yes
22.05.2021
Week 5 - sprint4 | Hamza | Hossein | Carlos | Ivan
Online |  | yes
02.06.2021
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## sprint1
Sprint Backlog : Sprint 1- to 30.04.2021
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Setup Github | 1 | All | FINISHED
Study the Videoes and materials | 1 | All | FINISHED
1. As an owner I want a platform that access the customers answers and compare them with candidate answers and recommend the 3-4 best matches. |  | Hossein
• create an algorithm which compare the customer answers with candidates answers. |  | Hossein | ONGOING |  | 1 |  | 1
* create required tables in databse |  | Hossein | FINISHED |  | 0.5 |  |  | 0.5
• calculate the percent of match |  | Hossein | ONGOING | 1 |  | 1
• save the result in a database use result set |  | Hossein | ONGOING |  |  |  | 1 | 0.5
2. As a customer I should be able to go back and forth thought questionary and change my answers if needed before submit. |  | Hossein
• create GUI for questions with html |  | Hossein | ONGOING | 1 | 1 |  | 0.5 | 1
• design question part with CSS |  | Hossein | ONGOING | 0.5 | 0.5 |  |  | 0.5
• save the customer answers to database after summation |  | Hossein | ONGOING |  |  |  | 1
• it needs next and previous buttons |  | Hossein | ONGOING |  |  | 1
3. As a customer I should see the result of my answers and suggested candidates with great user interface |  | Hossein
• create a html page for user interface which shows your result (in percent) with those three candidates |  | Hossein | ONGOING |  |  | 1 |  | 1
• need a connection to database to bring the suggested candidate’s data and customer answers to page |  | Hossein | ONGOING |  |  | 0.5 | 1.5 | 0.5
• need to design with CSS |  | Hossein | ONGOING |  |  |  | 1
* create related classes |  | Hossein | ONGOING |  |  |  |  | 1
* need connection with resultset |  | Hossein | ONGOING |  |  | 0.5 | 0.5 | 0.5
4. As a customer I should be able to see the Information of the candidates that have the best match with my answers with suitable user interface. |  | Hossein
• create a html page for user interface which shows the information of candidate |  | Hossein | ONGOING | 1 | 0.5 | 0.5 |  | 0.5
• need a connection to database to bring the suggested candidates’ data to page |  | Hossein | ONGOING |  | 0.5
• need to design with CSS |  | Hossein | FINISHED
• create page to see all candidates |  | Hossein | FINISHED |  | 1 | 1
5. As an owner I want to Candidate information and also candidates’ answers. |  | Hossein
* need a jsp page for user interface |  | Hossein | ONGOING | 1 | 1 |  | 1 | 1
* need connection with database use resultset |  | Hossein | ONGOING
need required classes |  | Hossein | ONGOING
need use of css for better user interface |  | Hossein | ONGOING |  | 1 | 0.5
• create page to see all candidates |  | Hossein | ONGOING | 1
TOTAL |  |  |  | 5.5 | 7 | 6 | 7.5 | 7

## sprint2
Sprint Backlog : Sprint 2 - to 15.05.2021
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
1. As an owner I want a platform that access the customers answers and compare them with candidate answers and recommend the 3-4 best matches. |  | Hossein
• create an algorithm which compare the customer answers with candidates answers. |  | Hossein | ONGOING | 0.5 |  | 0.5 | 0.5 | 1
• calculate the percent of match |  | Hossein | ONGOING | 0.5 |  | 1
• save the result in a database |  | Hossein | ONGOING |  |  |  |  | 1
2. As a customer I should be able to go back and forth thought questionary and change my answers if needed before submit. |  | Hossein
• create GUI for questions with html |  | Hossein | FINISHED | 1 | 1 |  |  | 1
• design question part with CSS |  | Hossein | FINISHED | 0.5 | 0.5 |  |  | 0.5
• save the customer answers to database after summation |  | Hossein | FINISHED |  |  |  | 1 | 1
• it needs next and previous buttons |  | Hossein | FINISHED |  |  | 1
3. As a customer I should see the result of my answers and suggested candidates with great user interface |  | Hossein
• create a html page for user interface which shows your result (in percent) with those three candidates |  | Hossein | ONGOING |  |  | 1 |  | 1
• need a connection to database to bring the suggested candidate’s data and customer answers to page |  | Hossein | ONGOING |  |  | 0.5 | 1.5 | 0.5
• need to design with CSS |  | Hossein | FINISHED | 0.5
* create related classes |  | Hossein | FINISHED |  |  | 1 | 1
* need connection with resultset |  | Hossein | ONGOING |  |  | 1
4. As a customer I should be able to see the Information of the candidates that have the best match with my answers with suitable user interface. |  | Hossein
• create a html page for user interface which shows the information of candidate |  | Hossein | ONGOING | 1 | 0.5 | 0.5 |  | 0.5
• need a connection to database to bring the suggested candidates’ data to page |  | Hossein | ONGOING |  | 0.5
• need to design with CSS |  | Hossein | ONGOING
• create page to see all candidates |  | Hossein | FINISHED |  | 1 | 1
create connection with database use resultset
8. as an owner I need Create login page for admins which could be able to edit candidate and questions |  | Hossein
• use resultset for connecting to database |  | Hossein | FINISHED |  | 0.5 |  | 1
• create a login page with need a html page which contains GUI of the form. |  | Hossein | FINISHED |  |  | 0.5 | 1 | 1
use database to check info |  |  | FINISHED
9. As an owner I should be able to create questionary, which customers can use it answer the questions. |  | Hossein
• use resultset for connecting to database |  | Hossein | FINISHED |  | 0.5 |  | 1
• create a login page with need a html page which contains GUI of the form. |  | Hossein | FINISHED |  |  | 0.5 | 1 | 1
create a functions for next and back buttons |  | Hossein | FINISHED
use database to check info |  |  | FINISHED
TOTAL |  |  |  | 4 | 4 | 8 | 6 | 7.5

## sprint3
Sprint Backlog : Sprint 3 - to 22.05.2021
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
1. As an owner I want a platform that access the customers answers and compare them with candidate answers and recommend the 3-4 best matches. |  | Hossein
• create an algorithm which compare the customer answers with candidates answers. |  | Hossein | ONGOING | 1 | 0.5 | 0.5 |  | 0.5
• calculate the percent of match |  | Hossein | ONGOING |  | 0.5
• save the result in a database |  | Hossein | FINISHED |  |  |  | 1
* need connection with database with resultset |  | Hossein | ONGOING
* create tables in my sql is needed |  | Hossein | FINISHED |  | 1
3. As a customer I should see the result of my answers and suggested candidates with great user interface |  | Hossein
• create a html page for user interface which shows your result (in percent) with those three candidates |  | Hossein | ONGOING |  |  | 1 |  | 1
• need a connection to database to bring the suggested candidate’s data and customer answers to page |  | Hossein | ONGOING |  |  | 2 | 1 | 0.5
• need to design with CSS |  | Hossein | FINISHED
* create related classes |  | Hossein | FINISHED
* need connection with resultset |  | Hossein | ONGOING |  | 1 | 1 | 1
4. As a customer I should be able to see the Information of the candidates that have the best match with my answers with suitable user interface. |  | Hossein
• create a html page for user interface which shows the information of candidate |  | Hossein | ONGOING | 1 | 0.5 | 0.5 |  | 0.5
• need a connection to database to bring the suggested candidates’ data to page |  | Hossein | ONGOING
• need to design with CSS |  | Hossein | ONGOING |  |  |  | 1 | 1
• create page to see all candidates |  | Hossein | FINISHED |  | 1 | 1
create connection with database use resultset |  | Hossein | ONGOING |  |  |  | 2 | 1
10. As a customer, I should be check my answers after finish my questionari |  | Hossein
• create a jsp page for user interface which shows question and answers |  | Hossein | FINISHED | 1 |  | 0.5 |  | 0.5
• need a connection to database with resultset |  | Hossein | FINISHED |  |  |  | 1
• need to design with CSS |  | Hossein | FINISHED |  |  |  |  | 0.5
• create class for customer and candidate answers |  | Hossein | FINISHED |  | 1 | 1
create a chart wich reads from database |  | Hossein | FINISHED
as a customer I need a navigation bar to access better throught pages |  | Hossein
Use bootstrap to create a navigation bar |  | Hossein | FINISHED | 1 |  | 0.5 |  | 0.5
• need a connection with links |  | Hossein | FINISHED |  |  |  | 1
• need to design with CSS |  | Hossein | FINISHED |  |  |  |  | 0.5
• try to be dynamic with use of jsp |  | Hossein | FINISHED |  | 1 | 1
TOTAL |  |  |  | 3 | 5.5 | 7.5 | 7 | 5.5

## sprint4
Sprint Backlog : Sprint 4 - to 02.06.2021
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
1. As an owner I want a platform that access the customers answers and compare them with candidate answers and recommend the 3-4 best matches. |  | Hossein
• create an algorithm which compare the customer answers with candidates answers. |  | Hossein | FINISHED |  |  | 0.5 |  | 0.5
• calculate the percent of match |  | Hossein | FINISHED
• save the result in a database |  | Hossein | FINISHED | 1 |  |  | 1
* need connection with database with resultset |  | Hossein | FINISHED
* create tables in my sql is needed |  | Hossein | FINISHED |  | 1
3. As a customer I should see the result of my answers and suggested candidates with great user interface |  | Hossein
• create a html page for user interface which shows your result (in percent) with those three candidates |  | Hossein | FINISHED |  |  | 1 |  | 1
• need a connection to database to bring the suggested candidate’s data and customer answers to page |  | Hossein | FINISHED |  | 1 |  | 1 | 0.5
• need to design with CSS |  | Hossein | FINISHED
* create related classes |  | Hossein | FINISHED
* need connection with resultset |  | Hossein | FINISHED |  | 1 | 0.5 | 1
4. As a customer I should be able to see the Information of the candidates that have the best match with my answers with suitable user interface. |  | Hossein
• create a html page for user interface which shows the information of candidate |  | Hossein | FINISHED | 1 |  | 0.5 |  | 0.5
• need a connection to database to bring the suggested candidates’ data to page |  | Hossein | FINISHED
• need to design with CSS |  | Hossein | FINISHED |  |  |  | 1 | 1
• create page to see all candidates |  | Hossein | FINISHED |  | 1 | 1
create connection with database use resultset |  | Hossein | FINISHED | 0.5 | 0.5
11. as an owner I need Create login page for admins which could be able to edit Candidates |  | Hossein
• create a html page for user interface which shows the information of candidate |  | Hossein | FINISHED | 1 | 0.5 |  |  | 0.5
• need a connection to database to bring the suggested candidates’ data to page |  | Hossein | FINISHED
• need to design with CSS |  | Hossein | FINISHED |  |  |  | 1 | 1
• create page to see all candidates |  | Hossein | FINISHED |  | 1
create connection with database use resultset |  | Hossein | FINISHED | 1
12 - as an owner I should be able to add new candidates with their answers |  | Hossein
• create a html page for user interface which shows the information of candidate |  | Hossein | FINISHED | 1 | 0.5 | 0.5 |  | 0.5
create connection with database use resultset |  | Hossein | FINISHED
• need to design with CSS |  | Hossein | FINISHED |  |  |  | 1 | 1
• create page to see all candidates use JSP |  | Hossein | FINISHED |  | 1 | 1
create connection with database use resultset |  | Hossein | FINISHED | 1
13 - as a customer I need to see statistics of candidates results |  | Hossein
• create a html page for user interface which shows result of candidate answers |  | Hossein | FINISHED | 1 | 0.5 | 0.5 |  | 0.5
• need a connection to database to bring the suggested candidates’ data to page with resultset |  | Hossein | FINISHED |  |  | 1 | 1
• need to design with CSS |  | Hossein | FINISHED
Use google developer to create charts |  | Hossein | FINISHED | 1 | 1 |  |  | 1
• create page to see all candidates with JSP |  | Hossein | FINISHED |  |  | 1 | 1
TOTAL |  |  |  | 8.5 | 9 | 7.5 | 8 | 8